LOGISTICS & IMPORT-EXPORT MANAGEMENT PLATFORM

Project Roadmap

Phases · Milestones · Gate Checkpoints

7 Phases  ·  24 Milestones  ·  7 Gate Checkpoints  ·  ~5 Months

Document date: 18 August 2026

# Project roadmap overview

This document structures the Cargo Track platform build into seven sequential phases, each ending at a concrete gate checkpoint. Gates are binary: either the condition is met or work continues in that phase. No gate may be bypassed.

The roadmap covers everything from design artifact completion (Phase 0, current position) through core backend implementation, shipping and warehousing logic, the document/payment pipeline, frontend delivery, and finally production deployment with portfolio polish.

| 7 Phases | 24 Milestones | 7 Gate checkpoints | ~5 mo Estimated duration |
| --- | --- | --- | --- |

## Deliverable tag legend

| Doc | Documentation artifact |
| --- | --- |
| Code | Implementation deliverable |
| Design | Visual / design artifact |
| Test | Testing / verification |
| Gate ✓ | Go / no-go checkpoint |

| 0 | Foundation & design artifacts | Weeks 1–2 |
| --- | --- | --- |

| ▸ | Requirements document finalized Interview notes consolidated, Part 9 outstanding questions resolved, and all assumptions confirmed with the domain expert. This is the single source of truth for domain rules throughout the build. Doc |
| --- | --- |

| ▸ | ERD signed off All 19 entities and 16 relationships reviewed. Junction tables (CONTAINER_ALLOCATIONS), self-referencing structure (DOCUMENTS.supersedes_id), and all append-only tables confirmed. No schema change proceeds without updating the ERD. Doc Design |
| --- | --- |

| ▸ | State diagrams complete Order lifecycle (8 states, 4 exception paths) and Container lifecycle (5 states, 1 sub-flow) delivered as Mermaid source for the repo and presentation-quality PNG for the portfolio. Doc Design |
| --- | --- |

| ▸ | Remaining system design diagrams Actor/swimlane flow diagram and NOTIFICATIONS retry pipeline diagram, both matching the established visual system (color-coding, arrow conventions, legend). Doc Design |
| --- | --- |

| ⚑ | Gate 0 — Design freeze All diagrams consistent and cross-referenced. Portfolio documentation package is presentable to a reviewer without additional explanation. No schema changes advance without updating ERD and state diagrams. |
| --- | --- |

| 1 | Local dev environment | Weeks 2–3 |
| --- | --- | --- |

| ▸ | Repo & monorepo structure Git repo initialized with workspace layout: /backend (NestJS or FastAPI), /frontend (Next.js), /infra (Docker Compose, migrations). Conventional commits enforced from day one. Code |
| --- | --- |

| ▸ | Docker Compose stack running postgres, redis, backend, and frontend services orchestrated locally. All connection strings via environment variables — no hardcoded Compose DNS hostnames. Health checks on all services. Code |
| --- | --- |

| ▸ | Database schema applied via migrations All 19 tables created through a migration tool (Flyway, Alembic, or Prisma). Seed script populates demo data covering all entity types. Schema fully version-controlled — no raw DDL in README. Code |
| --- | --- |

| ⚑ | Gate 1 — Dev baseline docker compose up from a clean clone reaches all services. Postgres tables exist. Redis responds. A fresh migration runs from scratch without error. |
| --- | --- |

| 2 | Core backend — orders & parties | Weeks 3–6 |
| --- | --- | --- |

| ▸ | Auth & role system JWT authentication with two roles: Office Manager (full access) and Client (read-only, scoped strictly to own orders). Middleware enforces data scoping — client A cannot access client B data under any request. Code Test |
| --- | --- |

| ▸ | Parties CRUD CLIENTS, SUPPLIERS, FREIGHT_PROVIDERS, and CUSTOMS_AGENTS endpoints. Passport scan upload for clients stores a file reference, not binary data in the database. Mandatory field validation per entity type. Code Test |
| --- | --- |

| ▸ | Orders & order items CRUD ORDERS and ORDER_ITEMS with full lifecycle field set including CBM/weight calculation helpers. Every money column carries an explicit currency field. Deposit percentage enforced at approximately 20%. Code Test |
| --- | --- |

| ▸ | Order state machine Status transitions enforced server-side — status is not a free string field. Every valid transition writes to STATUS_HISTORY with from_status, to_status, changed_by, and reason. Invalid transitions return HTTP 422. Code Test |
| --- | --- |

| ▸ | Production orders & QC inspections PRODUCTION_ORDERS linked to orders and suppliers. QC_INSPECTIONS with client_signed_off_at enforced as a hard prerequisite — the balance invoice cannot be raised until this timestamp is set. Code Test |
| --- | --- |

| ⚑ | Gate 2 — Order lifecycle covered A full order can be walked from Order Placed to Closed Out via API calls alone. All 8 states transition correctly. An invalid transition is rejected with a clear error. STATUS_HISTORY is populated at every step. |
| --- | --- |

| 3 | Shipping, containers & warehousing | Weeks 6–9 |
| --- | --- | --- |

| ▸ | Containers & container state machine CONTAINERS with 5-state lifecycle mirroring the state diagram. Transitions write to STATUS_HISTORY. The container closes only when every associated order has reached Closed Out — enforced server-side, not by convention. Code Test |
| --- | --- |

| ▸ | Consolidated shipping (CONTAINER_ALLOCATIONS) Many-to-many junction table allowing one container to carry multiple orders. CBM and weight allocated per order row. A capacity guard rejects any allocation that would cause the container to exceed its CBM or weight maximum. Code Test |
| --- | --- |

| ▸ | Transit legs TRANSIT_LEGS linked to containers, implementing the optional direct vs. transit route sub-flow from the container state diagram. Sequence ordering with arrived_at and departed_at timestamps per leg. Code |
| --- | --- |

| ▸ | Warehousing & stock records WAREHOUSES and STOCK_RECORDS with hold_reason as free text (no fixed taxonomy). Stock hold and release endpoints. received_at and released_at timestamps support seasonal hold tracking. Code |
| --- | --- |

| ⚑ | Gate 3 — Shipping lifecycle covered A container can be opened, allocated orders in a consolidated scenario, departed, optionally transited, arrived, and closed — but only after all allocated orders have closed. Capacity guard is tested at the boundary value. |
| --- | --- |

| 4 | Documents, payments & notifications | Weeks 9–12 |
| --- | --- | --- |

| ▸ | Documents with version chains DOCUMENTS table with self-referencing supersedes_id for version history. Upload endpoint stores file_ref. released_to_client_at is null until payment clears — enforced at read time on every request, not only at write time. Code Test |
| --- | --- |

| ▸ | Document release gate (strongest business rule) The documents endpoint checks payment status before returning file_ref to any client request. Payment delayed means file_ref is absent from the response entirely. An integration test verifies this gate cannot be bypassed by any request path. Code Test |
| --- | --- |

| ▸ | Payments CRUD PAYMENTS with payment_type (deposit / balance), direction, currency, counterparty_id, and paid_at. Deposit recorded on order confirmation. Balance payment triggers the document release gate to open. Code |
| --- | --- |

| ▸ | Notifications pipeline (BullMQ / Celery) Append-only NOTIFICATIONS table. Every status transition enqueues a background job. Each record carries retry_count, last_error, and a dead-letter status field. Failed jobs surface in the Office Manager dashboard. Worker service included in Docker Compose. Code Test |
| --- | --- |

| ▸ | CLIENT_DOCUMENTS & data retention Sensitive document references isolated in the CLIENT_DOCUMENTS table with retention_expires_at per record. A scheduled cleanup job removes expired references without deleting the underlying document from storage. Code |
| --- | --- |

| ⚑ | Gate 4 — Business rules verified Document withholding gate proven by an automated test that cannot be disabled. Deposit recorded on confirmation. Balance payment triggers release. The retry pipeline correctly cycles through failure, retry, and dead-letter states. |
| --- | --- |

| 5 | Frontend — dashboard & client portal | Weeks 10–14 |
| --- | --- | --- |

| ▸ | Next.js project scaffold + TanStack Query App router with environment-based API base URL. Two distinct route groups: /manager (full access) and /portal (client, read-only). Shared component library. Auth context with role-aware routing. Code |
| --- | --- |

| ▸ | Office Manager dashboard Orders list with status filter. Order detail view with status transition action buttons. Container allocation view showing CBM utilization. Notification inbox displaying retry status and failed job indicators. Code Design |
| --- | --- |

| ▸ | Client portal (read-only) Login scoped strictly to the client's own orders. Shipment status timeline view. Document download disabled and visually indicated as pending when payment has not cleared — not simply a missing button. Code Design |
| --- | --- |

| ⚑ | Gate 5 — End-to-end user journey The Office Manager can place and close an order entirely through the UI. A client logs in and sees only their own orders. Document download is visibly blocked until the balance payment is recorded in the system. |
| --- | --- |

| 6 | Portfolio polish & deployment | Weeks 14–18 |
| --- | --- | --- |

| ▸ | Bulk operations (portfolio showcase) Bulk status update endpoint with transactional rollback on partial failure. Bulk document release after a payment batch. Migration scripts with retry logic and structured error reporting. These demonstrate the backend engineering depth the project is built to showcase. Code Test |
| --- | --- |

| ▸ | Error handling & observability Structured error responses with consistent shape across all endpoints. Dead-letter queue visible in the dashboard. Request logging with correlation IDs. Health check endpoint used by deployment platform probes. Code |
| --- | --- |

| ▸ | Production deployment Deployed to Railway (managed Postgres and Redis plugins) or a VPS with docker compose. Environment variables replace all Compose DNS hostnames — DATABASE_URL and REDIS_URL injected by the platform. CI/CD pipeline runs migrations before each deploy. Code |
| --- | --- |

| ▸ | Portfolio README & case study README covers: domain story and interview source, architecture decisions, state machine design, bulk operations pattern, and notification retry design. Links to the live demo and all design artifact PDFs including this document. Doc Design |
| --- | --- |

| ⚑ | Gate 6 — Launch ready Live URL accessible with seed data loaded. Bulk operations demonstrated in the README with code references. All diagrams linked. A technical reviewer can walk the codebase from README to implementation without asking any questions. |
| --- | --- |

## Implementation notes

Current position

Phase 0 is in progress. The requirements document, ERD, and state diagrams are complete. The remaining two diagrams (actor/swimlane flow and NOTIFICATIONS retry pipeline) are the only outstanding items before Gate 0.

Phase overlap

Phases 2, 3, and 4 are backend-sequential. Phase 5 (frontend) can begin scaffolding while Phase 4 is in progress, once the API contracts from Phase 2 are stable.

Gate behavior

Gates are binary conditions, not reviews. Work stays in the current phase until the gate condition is fully satisfied. Gates should be verified by running the listed test or scenario, not by inspection.

Bulk operations

The bulk operations milestone in Phase 6 is the primary portfolio differentiation point. It should be prominently documented in the README, with the transactional rollback scenario explained and linked to the implementation.

Document withholding

The document release gate in Phase 4 is the strongest business rule in the domain. Its integration test should be the most complete test in the suite and should be referenced explicitly in the case study.

Environment portability

No service hostname is hardcoded at any phase. All connection details are read from environment variables. This ensures the Docker Compose local setup and the production platform share identical application code.